## initial summary
Issue # | Description | Status | Symptom | Fix Applied
1 | Book Now button does not link directly to selected flight but to airline homepage | Unresolved (Bug 001) | Clicking 'Book Now' takes user to airline website, but not directly to the selected flight | Tabled for future improvement; requires deeper investigation into airline URL structures
2 | Oxylabs API returns limited flight results (even when more are available on Google Flights) | Unresolved (Limitation 002) | Only 4 flights are returned despite requesting more (e.g., 10) | Implemented pagination, but API still limits results. Needs Oxylabs support confirmation
3 | SSL certificate verification error when calling Oxylabs API | Resolved | requests.exceptions.SSLError: CERTIFICATE_VERIFY_FAILED | Installed/upgraded OpenSSL, set correct Python SSL certificate path
4 | Unauthorized API error when calling Oxylabs API | Resolved | API Error: 401 - Unauthorized | Verified and corrected API credentials
5 | Oxylabs API 'google_flights' source not supported | Resolved | API Error: 400 - Unsupported source | Changed API source from 'google_flights' to 'universal'
6 | User cannot select return date for round-trip flights | Resolved | Selecting 'Round-trip' does not show return date input | Modified UI to dynamically show return date when 'Round-trip' is selected
7 | 'Direct' vs. 'Any' flight type filter not working | Resolved | Selecting 'Nonstop Only' still shows connecting flights | Added correct filtering logic to API payload and response processing
8 | API returns prices with commas, causing parsing error | Resolved | ValueError: invalid literal for int() with base 10: '1,011' | Modified code to remove commas before converting price to integer
9 | Dynamic selection of 'Top N' flights instead of fixed Top 3 | Resolved | Previously hardcoded Top 3 flights, now user can select 3-10 flights | Added slider input for user selection and updated display logic
10 | API results showing fewer flights than expected despite pagination | Resolved | Pagination was not applied properly, resulting in only first-page results | Modified response processing to merge results from multiple pages

## updated_summary
Issue # | Description | Status | Symptom | Fix Applied | Code Snippet
1 | Book Now button does not link directly to selected flight but to airline homepage | Unresolved (Bug 001) | Clicking 'Book Now' takes user to airline website, but not directly to the selected flight | Tabled for future improvement; requires deeper investigation into airline URL structures | N/A
2 | Oxylabs API returns limited flight results (even when more are available on Google Flights) | Unresolved (Limitation 002) | Only 4 flights are returned despite requesting more (e.g., 10) | Implemented pagination, but API still limits results. Needs Oxylabs support confirmation | payload['pages'] = 2 # Request more pages
3 | SSL certificate verification error when calling Oxylabs API | Resolved | requests.exceptions.SSLError: CERTIFICATE_VERIFY_FAILED | Installed/upgraded OpenSSL, set correct Python SSL certificate path | import certifi requests.post(API_URL, json=payload, verify=certifi.where())
4 | Unauthorized API error when calling Oxylabs API | Resolved | API Error: 401 - Unauthorized | Verified and corrected API credentials | response = requests.post(API_URL, auth=(os.getenv('OXYLABS_USERNAME'), os.getenv('OXYLABS_PASSWORD')))
5 | Oxylabs API 'google_flights' source not supported | Resolved | API Error: 400 - Unsupported source | Changed API source from 'google_flights' to 'google_search' | payload['source'] = 'google_search'
6 | User cannot select return date for round-trip flights | Resolved | Selecting 'Round-trip' does not show return date input | Modified UI to dynamically show return date when 'Round-trip' is selected | if trip_type == 'Round-trip': return_date = st.date_input('Select Return Date', departure_date + timedelta(days=7))
7 | 'Direct' vs. 'Any' flight type filter not working | Resolved | Selecting 'Nonstop Only' still shows connecting flights | Added correct filtering logic to API payload and response processing | if flight_type == 'Nonstop Only': flights = [f for f in flights if f['type'].lower() == 'nonstop']
8 | API returns prices with commas, causing parsing error | Resolved | ValueError: invalid literal for int() with base 10: '1,011' | Modified code to remove commas before converting price to integer | price = int(flight['price'].replace('$', '').replace(',', ''))
9 | Dynamic selection of 'Top N' flights instead of fixed Top 3 | Resolved | Previously hardcoded Top 3 flights, now user can select 3-10 flights | Added slider input for user selection and updated display logic | top_n = st.slider('Select number of top flights:', 3, 10, 3)
10 | API results showing fewer flights than expected despite pagination | Resolved | Pagination was not applied properly, resulting in only first-page results | Modified response processing to merge results from multiple pages | for result in data['results']: flights.extend(result['content']['results']['flights']['results'])
11 | Parsing issue when 'd' (days) is present in flight duration | Resolved | Crash when processing flights with durations like '1d 6h' | Updated parsing logic to handle both days and hours | duration = sum(int(x[:-1]) * (24 if 'd' in x else 1) for x in flight['duration'].split())
12 | Hardcoded username/password in the script | Resolved | Security risk: credentials stored directly in code | Replaced with environment variables using os.getenv() | username = os.getenv('OXYLABS_USERNAME')
13 | Plan to switch from Oxylabs to Skyscanner API | Enhancement Request | Oxylabs has limitations; may not be the best choice long-term | Documented as future enhancement | N/A
14 | Need to store information in SQLite instead of local memory | Enhancement Request | MVP stores everything in memory; no persistence | Documented as future enhancement | N/A
15 | cURL request to use env variables resulted in error | Resolved | Invalid type for parameter render | Changed render parameter to 'HTML' | -H 'Content-Type: application/json' -d '{"render": "html"}'
16 | VS Code virtual environment not recognized | Resolved | Virtual environment packages not detected in VS Code | Configured VS Code interpreter and session to use correct virtual environment | Set Python interpreter in VS Code settings to virtual env path